## Slide 1: Overall Project Timeline
Activity | Week | 1 | 2 | 3 | 4 |  | 5 | 6 |  | 7 | 8
 | Date | 6/16 | 6/23 | 6/30 | 7/7 |  | 7/14 | 7/21 |  | 7/28 | 8/4
Kickoff & Alignment |  |  |  |  |  |  |  |  |  |  | 
Stakeholder Interviews |  |  |  |  |  |  |  |  |  |  | 
Argano Data Analysis |  |  |  |  |  |  |  |  |  |  | 
Competitive Research |  |  |  |  |  |  |  |  |  |  | 
Qualitative Research Design |  |  |  |  |  |  |  |  |  |  | 
Qualitative Interviews |  |  |  |  |  |  |  |  |  |  | 
Quantitative Research Design |  |  |  |  |  |  |  |  |  |  | 
Quantitative Data Collection |  |  |  |  |  |  |  |  |  |  | 
Analysis & Results Development |  |  |  |  |  |  |  |  |  |  | 
Recommendations Delivery |  |  |  |  |  |  |  |  |  |  | 
Board Meeting Prep
Final Delivery
Today
Launch survey